## Jul-2013
Project Name | RDC-Java |  |  | Status Update Chart
SL | Ticket ID | Ticket Name/Parameter | Assign Date | Problem Description | Reason | Action | Key | Last Submit Date | Status | Client Comment
1 | SYS-7921 | dea_fugitives.groovy indexUrl="http://www.justice.gov/dea/fugitives/wdo/wdo_div_list.shtml" | 2013-07-08 | 31 [main] INFO [UrlRequestInvoker.java:150] : user[] Invoking[http://www.usdoj.gov/dea/fugitives/wdo/wdolist.htm] main" java.lang.Exception: Error invoking[http://www.usdoj.gov/dea/fugitives/wdo/wdolist.htm] HTTP/1.0 404 Not Found | na | Regex Fix and changed url. Old url : http://www.usdoj.gov/dea/fugitives/wdo/wdolist.htm (HTTP/1.0 404 Not Found) replace by - New url: http://www.justice.gov/dea/fugitives/wdo/wdo_div_list.shtml | dea_ fugitives_washignton | 2013-07-11 | ok

## jun-2013
Project Name | RDC-Java |  |  | Status Update Chart
SL | Ticket ID | Ticket Name/Parameter | Assign Date | Problem Description | Reason | Action | Additional Comment | Last Submit Date | Status | Client Comment
1 | SYS-7774 | us_af_office_special_investigation.groovy | 2013-06-11 | SYS-7774 us_af_office_special_investigation - IMPORT_FAILURE - 2013/05/29 18:00:07:705 EDT Failure Details: StackTrace: java.lang.NullPointerException: Cannot invoke method getAt() on null object at org.codehaus.groovy.runtime.NullObject.invokeMethod(NullObject.java:77) at org.codehaus.groovy.runtime.InvokerHelper.invokePogoMethod(InvokerHelper.java:784) | na | * Fixed regex statements * Added PDF parser functionality * Works fine now | na | 2013-06-12 | ok

## may-2013
Project Name | RDC-Java |  |  | Status Update Chart
SL | Ticket ID | Ticket Name/Parameter | Assign Date | Problem Description | Reason | Action | Additional Comment | Last Submit Date | Status | Client Comment
1 | SYS-7626 | forfeiture_gov.groovy archiveDirectory="/SG/Internal_Data/Web_Archive/forfeiture.gov/" archiveUrl="http://archive.rdc.com/forfeiture.gov/100c1d0848c40504.html" | 2013-05-07 | SYS-7626 forfeiture_gov java.lang.NullPointerException: Cannot invoke method getAt() on null object at org.codehaus.groovy.runtime.NullObject.invokeMethod(NullObject.java:77) at org.codehaus.groovy.runtime.InvokerHelper.invokePogoMethod(InvokerHelper.java:784) at org.codehaus.groovy.runtime.InvokerHelper.invokeMethod(InvokerHelper.java:758) | na | * Missing post parameters are included with some regex fixes. * ArchiveUrl "http://archive.rdc.com/forfeiture.gov/100c1d0848c40504.html" contains some pdf links which are not fetch-able from my side or they are dead/damaged. * Other than archiveurl issue, this script works fine now. | na | 2013-05-07 | ok
2 | SYS-7633 | (not available) | 2013-05-07 | SYS-7633 dea_fugitives_intl java.lang.Exception: Unable to locate[dea_fugitives_intl] at com.rdc.importer.scrapian.resolver.SubversionScrapianResolver.resolveScript(SubversionScrapianResolver.java:46) at com.rdc.importer.scrapian.resolver.DelegatingScrapianResolver.resolveScript(DelegatingScrapianResolver.java:31) at com.rdc.importer.scrapian.ScrapianEngine.scrape(ScrapianEngine.java:103) | na | * I haven't found any key named "dea_fugitives_intl" in "scrapian-config-prod.xml". * So this error "Unable to locate[dea_fugitives_intl]" is most likely because of the unavailability of the key named "dea_fugitives_intl". | na | 2013-05-07 | ok
3 | SYS-7305 | us_ca_sex_offenders.groovy | 2013-05-12 | SYS-7305 - Scraper Fix Needed for Monitored List: CA Office of the Attorney General - Sex Offenders The "CA Office of the Attorney General - Sex Offenders" monitored list contains entity URLS in the records that we created that go to dead URLS. I surmised that this might be because the base URL for this site - http://www.meganslaw.ca.gov/disclaimer.aspx?lang=ENGLISH - requires online users to first agree to the disclaimer and terms of use. Can we confirm if that is the case? If it is, we should provide ONLY this "base" URL to our clients, since the internal URL is un-usable to an end user. It's also critical to have a functioning URL for our MARS analysts so that when they drill down to look at the source for a possible alert, they can get to the record. | na | * Some of html parts changed with some url-params added. * All changes are updated. * Works fine now. | na | 2013-05-15 | ok
4 | SYS-7349 | us_al_sex_offenders.groovy | 2013-05-12 | SYS-7349 - Scraper Fix Needed for Monitored List: AL Department of Public Safety - Sex Offenders 4,331 deleted records for the captioned list in DQA. Sampled records still appear on the state's website. Please advise. Current URL for this list: http://dps.alabama.gov/community/wfsexoffendersearch.aspx (the URL that's in DQA is incorrect - unsure as to whether we're using that for our scraper) | na | * Regex and some other fixes. * Works fine now. | na | 2013-05-15 | ok
5 | SYS-7578 | ca_cto_individuals.groovy | 2013-05-12 | SYS-7578 - Broken Scraper - Canada Securities Administrators Cease Trade - Individuals This scraper (source key: ca_cto_individuals) is not functioning properly. It is capturing "words" that are not entities. Furthermore, it is capturing multiple names and "AKAs" (aliases) into ONE name field, rather than parsing them separately. Examples include entities named: AND AMR I ALSO KNOWN ELGINDY , ANTHONY , ELGINDY , TONY , AND PACIFIC , ANTHONY ELGINDY | na | * All the broken codes were fixed. * It now captures valid entities name in correct format. | na | 2013-05-21 | ok
6 | SYS-7326 | us_ks_sex_offenders.groovy | 2013-05-16 | SYS-7326 Scraper Fix Needed for Monitored List: Kansas Sex Offenders "Our scraper has two issues that need addressing: a) It is not parsing the entity names correctly which could cause names to be missed by our name matching system. First and last names are separated by a comma but no space between them, e.g. AARON CHARLES,COOK AARON EUGENE,CREECH It appears this is the way the source records themselves appear, so am not sure if we can work around that and replace the comma with a space? b) None of the records appear to have the STATE field filled in, even though CITY and POSTAL CODE. Looking at the source records, most have KS as the state, so we should capture that in the STATE field. FYI, the updated URL for this site (since the one in the DQA info page is incorrect) is: http://www.kbi.ks.gov/registeredoffender/" | na | * Kansas Sex Offenders site uses "captcha validation" which is not yet supported by our java codebase. * So this script can not be resolved untill such functionality to read capatcha is implemented. | na | 2013-05-24 | ok
7 | SYS-7327 | id_financial_actions.groovy indexUrl="http://finance.idaho.gov/ConsumerFinance/AdministrativeActions.aspx" siteType="Consumer Finance" baseUrl="http://finance.idaho.gov/ConsumerFinance/" | 2013-05-16 | SYS-7327 Scraper Fix Needed for Monitored List: ID Dept. of Finance - Consumer Finance Actions "Not a major issue, but the ID Dept. of Finance - Consumer Finance Actions has two records that picked up extraneous information in the name field - unclear whether this is something we can work around given the strange way the names at the source URL are parsed. In any case, if it's fixable, here are the two records where the problem appeared: Entity Name Captured in DQA: ""Edie Webber, husband"" Entity Name Captured in DQA: ""wife"" These both come from the same entry at the main source URL: # 2012-9-20 - Brian Webber, and Edie Webber, husband and wife, dba Clean Slate Credit Services - Consent Order Main source URL: http://finance.idaho.gov/ConsumerFinance/AdministrativeActions.aspx" | na | * All codes are fixed to parse entities in correct format. * Works fine now. | na | 2013-05-29 | ok
8 | SYS-7770 & SYS-7771 | ofac_sdn_removed.groovy | 2013-05-30 | SYS-7770 One of our systemically scraped Monitored Lists - the OFAC Removed Entries List (source key: OFAC_REMOVED_LIST) has default coding of WLT / ASC. We need to change the default risk coding for that list to FOF / ASC. SYS-7771 The OFAC REmoved Entities list has not been updated since June 2012. | na | * Regex fixes to captures all data urls. * Data file(.txt) contains garbage and malformed data so it is difficult to write regex statements for data lines. | na | 2013-06-14 | ok

## apr-2013
Project Name | RDC-Java |  |  | Status Update Chart
SL | Ticket ID | Ticket Name/Parameter | Assign Date | Problem Description | Reason | Action | Additional Comment | Last Submit Date | Status | Client Comment
1 | SYS-6286 | crimestoppers_dynasites.groovy | 2013-04-02 | SYS-7520 crimestoppers_dynasites - IMPORT_FAILURE java.lang.ArrayIndexOutOfBoundsException | na | * Regex fixed * Works fine now | na | 2013-04-03 | ok
2 | SYS-7530 | key: uk_london_gazette_winding_up_petitions_companies ( 327 entities ) ====================================================================== uk_london_gazette.groovy indexUrl="http://www.london-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-court/petitions-companies/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/london-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/london-gazette.co.uk/" archiveFilename="winding-up-petitions-companies.html" key: uk_london_gazette_winding_up_petitions_partnerships ((10 - 1 duplicate) = 9 entities) ========================================================================================== uk_london_gazette.groovy indexUrl="http://www.london-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-court/petitions-partnerships/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/london-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/london-gazette.co.uk/" archiveFilename="winding-up-petitions-partnerships.html" key: uk_london_gazette_winding_up_orders_companies ( 109 entities ) =================================================================== uk_london_gazette.groovy indexUrl="http://www.london-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-court/orders-companies/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/london-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/london-gazette.co.uk/" archiveFilename="winding-up-orders-companies.html" key: uk_london_gazette_winding_up_orders_partnerships ( 2 entities ) ===================================================================== uk_london_gazette.groovy indexUrl="http://www.london-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-court/orders-partnerships/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/london-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/london-gazette.co.uk/" archiveFilename="winding-up-orders-partnerships.html" key: uk_london_gazette_appointment_of_liquidators ( 25 entities ) ================================================================== uk_london_gazette.groovy indexUrl="http://www.london-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-court/appointments/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/london-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/london-gazette.co.uk/" archiveFilename" value="appointment-of-liquidators.html" key: uk_london_gazette_notices_to_creditors ( 7 entities ) ========================================================== uk_london_gazette.groovy indexUrl="http://www.london-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-court/creditors/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/london-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/london-gazette.co.uk/" archiveFilename="notices-to-creditors.html" key: uk_edinburgh_gazette_resolutions_for_winding_up ( 42 entities ) ==================================================================== uk_london_gazette.groovy indexUrl="http://www.edinburgh-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-members/resolution/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/edinburgh-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/edinburgh-gazette.co.uk/" archiveFilename="resolutions-for-winding-up.html" key: uk_edinburgh_gazette_appointment_of_receivers ( 6 entities ) ================================================================= uk_london_gazette.groovy indexUrl="http://www.edinburgh-gazette.co.uk/issues/recent/10/corp-insolvency-receivership/appointments/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/edinburgh-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/edinburgh-gazette.co.uk/" archiveFilename="appointment-of-receivers.html" key: uk_edinburgh_gazette_appointment_of_liquidators ( 43 entities ) ==================================================================== uk_london_gazette.groovy indexUrl="http://www.edinburgh-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-members/appointments/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/edinburgh-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/edinburgh-gazette.co.uk/" archiveFilename="appointment-of-liquidators.html" key: uk_edinburgh_gazette_notices_to_creditors ( 7 entities ) ============================================================= uk_london_gazette.groovy indexUrl="http://www.edinburgh-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-members/creditors/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/edinburgh-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/edinburgh-gazette.co.uk/" archiveFilename="notices-to-creditors.html" key: uk_belfast_gazette_appointment_of_administrators ( 5 entities ) ==================================================================== uk_london_gazette.groovy indexUrl="http://www.belfast-gazette.co.uk/issues/recent/10/corp-insolvency-administration/appointments/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/belfast-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/belfast-gazette.co.uk/" archiveFilename="appointment-of-administrators.html" key: uk_belfast_gazette_administration_orders ( 0 entities ) ======================================================= uk_london_gazette.groovy indexUrl="http://www.belfast-gazette.co.uk/issues/recent/10/corp-insolvency-administration/orders/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/belfast-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/belfast-gazette.co.uk/" archiveFilename="administration-orders.html" key: uk_belfast_gazette_meetings_of_creditors ( 1 entities ) ============================================================ uk_london_gazette.groovy indexUrl="http://www.belfast-gazette.co.uk/issues/recent/10/corp-insolvency-administration/meetings-creditors/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/belfast-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/belfast-gazette.co.uk/" archiveFilename="meetings-of-creditors.html" key: uk_belfast_gazette_winding_up_petitions_companies ( 25 entities ) ====================================================================== uk_london_gazette.groovy indexUrl="http://www.belfast-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-court/petitions-companies/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/belfast-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/belfast-gazette.co.uk/" archiveFilename="winding-up-petitions-companies.html" key: uk_belfast_gazette_winding_up_petitions_partnerships ( 1 entities ) uk_london_gazette.groovy indexUrl="http://www.belfast-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-court/petitions-partnerships/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/belfast-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/belfast-gazette.co.uk/" archiveFilename="winding-up-petitions-partnerships.html" key: uk_belfast_gazette_winding_up_orders_companies ( 13 entities ) uk_london_gazette.groovy indexUrl="http://www.belfast-gazette.co.uk/issues/recent/10/corp-insolvency-winding-up-court/orders-companies/start=" archiveDirectory="/SG/Internal_Data/Web_Archive/belfast-gazette.co.uk/" archiveBaseUrl="http://archive.rdc.com/belfast-gazette.co.uk/" archiveFilename="winding-up-orders-companies.html" | 2013-04-05 | SYS-7530 uk_belfast_gazette_meetings_of_creditors – IMPORT_FAILURE | na | * Well, overall this script runs fine with few regex fixes. * But it fetches data from RDC archive url : "http://archive.rdc.com/belfast-gazette.co.uk/meetings-of-creditors.html" which have some "unnecessary" data in entity names (as I suspect so, IE: "Meeting of Creditors"). * I could have fixed it but as these data are from RDC archive file, so I didn't change it. * I'd appreciate your feedback on this issue. * Other than above issues, it works fine now. | na | 2013-04-15 | ok
3 | SYS-7537 | apra_disqualification.groovy | 2013-04-08 | SYS-7537 apra_disqualification - IMPORT_FAILURE at scrapian_scripts.apra_disqualification.run(apra_disqualification:14) | na | * This script works fine here. * Please check my current script. * If it doesn't work then I would appreciate if you send me a few more lines of logs. | na | 2013-04-08 | ok
4 | SYS-7538 | us_nj_dcj_most_wanted_fugitives.groovy | 2013-04-08 | SYS-7538 us_nj_dcj_most_wanted_fugitives java.lang.Exception: Monitored List for Item=[us_nj_dcj_most_wanted_fugitives] is empty. Verify url or website has not changed. | na | * Index url "http://www.dcjfugitives.org" returns blank page. * I tried to find alternative links but main "http://www.nj.gov/oag/nj-most-wanted.htm" site return to same link. * So I found no way to solve this issues. | na | 2013-04-12 | ok
5 | Forfeiture.gov | forfeiture_gov.groovy archiveDirectory="/SG/Internal_Data/Web_Archive/forfeiture.gov/" archiveUrl="http://archive.rdc.com/forfeiture.gov/100c1d0848c40504.html" | 2013-04-15 | Forfeiture.gov is not working correctly. The URL http://www.forfeiture.gov/AdvancedNoticeSearch.aspx is still good however it appears that certain .Net related controls changed and all you get is "Your request not found" page. PDF's are still downloadable. Please start with URL provided above and parse out parameters from Judicial District drop down, then use those parameters to conduct search and fetch pages. You will need to parse __VIEWSTATE, __EVENTVALIDATION for your POST parameters. Also you will have to add to your POST params ctl00$Main$uxSubmitSearchButton=Search+Notices and ctl00$Main$uxJudicialDistrictDropDownList=<YOUR DISTRICT CODE COMES HERE> | na | * Missing post parameters are included with some regex fixes. * ArchiveUrl "http://archive.rdc.com/forfeiture.gov/100c1d0848c40504.html" contains some pdf links which are not fetch-able from my side or they are dead/damaged. * Other than archiveurl issue, this script works fine now. | na | 2013-04-17 | ok

## mar-2013
Project Name | RDC-Java |  |  | Status Update Chart
SL | Ticket ID | Ticket Name/Parameter | Assign Date | Problem Description | Reason | Action | Additional Comment | Last Submit Date | Status | Client Comment
1 | SYS-6286 | us_mt_sex_offenders.groovy | 2013-03-01 | SYS-6286 us_mt_sex_offenders - IMPORT_FAILURE javax.net.ssl.SSLHandshakeException: sun.security.validator.ValidatorException: PKIX path building failed: sun.security.provider.certpath.SunCertPathBuilderException: unable to find valid certification path to requested target at us_mt_sex_offenders.run(us_mt_sex_offenders:10) | na | * Base url updated. * Works fine now. | na | 2013-03-01 | ok
2 | SYS-5991 | crimestoppers_dynasites.groovy | 2013-03-01 | SYS-5991 crimestoppers_dynasites - IMPORT_FAILURE java.lang.Exception: Error invoking[http://lamarcountycrimestoppers.com/wanteds.aspx] HTTP/1.1 404 Not Found | na | * The Top level URL - http://crimestoppersweb.com/links.aspx has more urls than the current script contains. * Some url has different page format than "wanteds.aspx" url, those are commented as some old code suggests. * Current fixed version works fine even though it's functionality can be extended. * I'll appreciate your any feedbacks on this issues. | na | 2013-03-05 | ok
3 | SYS-7281 | interpol_un_notices_individuals.groovy | 2013-03-05 | SYS-7281 interpol_un_notices_individuals - IMPORT_FAILURE java.lang.Exception: Monitored List for Item=[interpol_un_notices_individuals] is empty. Verify url or website has not changed. | na | * Index url updated. * Regex fixes. * Works fine now. | na | 2013-03-06 | ok
4 | SYS-7276 | us_nj_sex_offenders.groovy | 2013-03-05 | SYS-7276 us_nj_sex_offenders - IMPORT_FAILURE https://www6.state.nj.us/LPS_spoff/SetSession] HTTP/1.1 404 Not found new URL http://www.njsp.org/info/reg_sexoffend.html Regarding nj_sex_offenders list search please use geographic search on page https://www16.state.nj.us/LPS_spoff/geographicsearch.jsp Parse out county names and use them to collect offender names. | na | * All urls were updated with few changes. * Works fine now. | na | 2013-03-07 | ok
5 | SYS-7280 | interpol_un_notices_entities.groovy | 2013-03-05 | SYS-7280 interpol_un_notices_entities - IMPORT_FAILURE java.lang.Exception: Monitored List for Item=[interpol_un_notices_entities] is empty. Verify url or website has not changed. | na | * Url update. * Regex fixes. * Works fine now. | na | 2013-03-07 | ok
6 | SYS-6792 | us_tx_attorney_general.groovy | 2013-03-12 | SYS-6792 us_tx_attorney_general - IMPORT_FAILURE java.lang.Exception: Error invoking[http://www.oag.state.tx.us/criminal/cj_fugitives/cj_fugitive_all.php?newer=Latest] HTTP/1.1 404 Not Found | na | * Url and html updated. * Regex fixes. | na | 2013-03-14 | ok
7 | SYS-6801 | nv_gaming_excluded_persons.groovy baseUrl="http://gaming.nv.gov/" | 2013-03-12 | SYS-6801 nv_gaming_excluded_persons - IMPORT_FAILURE java.lang.Exception: Error invoking[http://gaming.nv.gov/loep_main.htm] HTTP/1.1 404 Not Found | na | * Index url and html updated. * Regex fixes. | na | 2013-03-15 | ok
8 | SYS-2674 | us_or_sex_offenders.groovy | 2013-03-18 | SYS-2674 oregon sex offenders site. us_or_sex_offenders.groovy script runs without errors but collects nothing. See if you can make it better. Removing LabelValueParser would definitely make it better :) | na | * The script runs fine and generate 678 entities. * I have fixed some of issues. * Present LabelValueParser implementation works fine for this script so I didn't edit it. * Please check the attached script and if it doesn't work as expected then I'll appreciate if you would provide me with few lines of log so that I could better debug the code. * It works fine at my side. | na | 2013-03-19 | ok
9 | SYS-6766 | colorado_mortgage_broker.groovy indexUrl="http://www.dora.state.co.us/Real-Estate/mortgage/disciplinary_action.htm" unlisted1="http://www.dora.state.co.us/Real-Estate/mortgage/disciplinary_action_2008.htm" | 2013-03-18 | SYS-6766 colorado_mortgage_broker - IMPORT_FAILURE java.lang.NullPointerException | na | * I couldn't access http://www.dora.state.co.us, I assume the server is down. * I invetigated the parent site: www.colorado.gov, but unfortunately couln't find any equivalent url. | na | 2013-03-19 | ok
10 | SYS-6017 | us_ga_re.groovy type="suspensions" | 2013-03-21 | SYS-6017 us_ga_re_suspensions – IMPORT_FAILURE | na | * Pdf contents updated. * Regex fixes. | na | 2013-03-21 | ok
11 | SYS-7074 | us_ca_online_escrow_fraud.groovy indexUrl="http://www.corp.ca.gov/FSD/fraud/2006.asp" year="2006" | 2013-03-21 | SYS-7074 us_ca_online_escrow_fraud_2006 - IMPORT_FAILURE looks like URL changed. And HTML probably too. Please investigate and fix if appropriate. | na | * It is an old problem, index url returns 404 error. * "http://www.corp.ca.gov/FSD/" contains no alternative url. | na | 2013-03-21 | ok
12 | SYS-6540 | us_me_securities_admin_orders.groovy | 2013-03-22 | SYS-6540 us_me_securities_admin_orders - IMPORT_FAILURE java.lang.StringIndexOutOfBoundsException: String index out of range: 32771 at us_me_securities_admin_orders.handleIndexPage(us_me_securities_admin_orders:11) | na | * Previous script was capturing garbage. * Works fine now. | na | 2013-03-27 | ok
13 | SYS-6756 | us_mn_real_estate_actions.groovy indexUrl="http://maine.gov/pfr/professionallicensing/professions/real_estate/discipline_index.shtml" year="2010" | 2013-03-22 | SYS-6756 us_mn_real_estate_disc_actions_2010 – IMPORT_FAILURE | na | * IndexUrl updated, so the html. * Regex fixes. * Works fine now. | na | 2013-03-28 | ok

## fab-2013
Project Name | RDC-Java |  |  | Status Update Chart
SL | Ticket ID | Ticket Name/Parameter | Assign Date | Problem Description | Reason | Action | Additional Comment | Last Submit Date | Status | Client Comment
1 | SYS-7126 | lapd_us_most_wanted.groovy | 2013-02-02 | SYS-7126 lapd_us_most_wanted - IMPORT_FAILURE java.lang.NullPointerException: Cannot invoke method contains() on null object at lapd_us_most_wanted$_handleEntityPage_closure3.doCall(lapd_us_most_wanted:46) at lapd_us_most_wanted.handleEntityPage(lapd_us_most_wanted:39) | na | * I haven´t got this exception and It did wokrd fine without any fixing. * Yet I have added !StringUtils.isBlank(entityName) check at line 46. * It works fine now. | na | 2013-02-04 | ok
2 | SYS-6957 | us_ak_sex_offenders.groovy | 2013-02-05 | SYS-6957 us_ak_sex_offenders - IMPORT_FAILURE java.lang.IllegalArgumentException: Invalid uri 'http://www.dps.state.ak.us/sorweb/sorweb.aspx">SOCKR Home Page</a></td> <td align="center" width="50%"><img src="/images/gray_arrow_wide.gif" width="25" height="12" alt="Next Page"> <a href="sorcra2.aspx': escaped absolute path not valid at us_ak_sex_offenders.handleIndexpage(us_ak_sex_offenders:28) | na | * Html changes,so some updates on codes. * Works fine now. | na | 2013-02-12 | ok
3 | SYS-7164 | us_vt_sex_offenders.groovy | 2013-02-05 | SYS-7164 us_vt_sex_offenders - IMPORT_FAILURE java.lang.Exception: Error invoking[https://secure.vermont.gov/DPS/sor/agreement.php] HTTP/1.1 404 Not Found | na | * Index url and related html changed so I have to built the script from scratch. * Works fine now. | na | 2013-02-22 | ok
4 | SYS-5937 | colorado_real_estate.groovy indexUrl="http://www.dora.state.co.us/Real-estate/real_estate/disciplinary_action2008.htm" | 2013-02-06 | SYS-5937 colorado_real_estate_2008 - IMPORT_FAILURE at colorado_real_estate_2008.handleIndexPage(colorado_real_estate_2008:11) at colorado_real_estate_2008.run(colorado_real_estate_2008:8) | na | * Web site shows "Gateway Timeout" error. Server might be temporarily down. * Everything should work fine when server come back again. Resubmission: 25/02/2013 ------------------------ * The only relevant URL that I have found is : http://www.colorado.gov/cs/Satellite/DORA-DRE/CBON/DORA/1251630412759 * But this URL only list - 1. 3 pdf files for "current year" while my requirement is of year 2008 2. Search link of entities which uses "captcha" in first page and I don't see any way implemented in our code-base to auto handle captchas. 3. Even if we can bypass captchas check we still don't get entities by year number. The only way I see to do this is brute searching all the data via search link by first¦last name then filter all those entities by desired year number but before that we need to bypass captcha codes automatically. So I forward this issue to your for any further instructions. | na | 2013-02-25 | ok
5 | SYS-5952 | us_ca_ebs.groovy | 2013-02-06 | SYS-5952 us_ca_ebs - IMPORT_FAILURE java.lang.Exception: Error invoking[http://www.corp.ca.gov/FSD/pdf/ebs.pdf] HTTP/1.1 404 Not Found | na | * Pdf url update. * Converted text were all scattered around. So I had to rewrite the entire handlePdf method. * Work fine now. | na | 2013-02-25 | ok
6 | us_il_sex_offenders | us_il_sex_offenders.groovy And forfeiture_gov.groovy | 2013-02-09 | RE: Sex Offender appears as address orphan From: Oleg KozlovskyAdd to Contacts Sent: Sat, Feb 9, 2013 at 1:42 am To: md.omar@servicengine.net Cc: Anne Jablonski, Tom Fogarty, JamesLin, Chris Correale image001.jpg (3.9 KB) Omar, Please take a look. To: James Lin; Oleg Kozlovsky Cc: Anne Jablonski Subject: RE: Sex Offender appears as address orphan Hi Guys, This seems to be a similar issue from forfeiture,gov. All GRID has is Christopher Jones, Illinois, while site has:: 4119 W 21st St, located in Chicago, IL. Not sure if this is manual or systematic. To: Oleg Kozlovsky Cc: Tom Fogarty; Anne Jablonski Subject: RE: Sex Offender appears as address orphan Oleg, Could you create a Jira and add this to the web scraper/list importer work queue for Oma? Thanks, James | na | Status: us_il_sex_offenders.groovy * Fixed address issue to capture it in correct form. * I have attached the script with the mail. * Works fine now Status: forfeiture_gov.groovy * This script deals with archiveUrl="http://w-tlapp02.rdc.com/SG/rep_Internal_Data/Web_Archive/forfeiture.gov/100c1d0848c40504.html" which I can't access from my side. * So I couldn't work on it. | * This ticket consist of two tickets(see description) | 2013-02-12 | ok
7 | SYS-6546 | us_ca_online_escrow_fraud.groovy indexUrl="http://www.corp.ca.gov/FSD/fraud/2004.asp" year="2004" | 2013-02-19 | SYS-6546 us_ca_online_escrow_fraud_2004 - IMPORT_FAILURE java.lang.Exception: Error invoking[http://www.corp.ca.gov/FSD/fraud/2004.asp] HTTP/1.1 404 Not Found | na | * This is an old problem. Index url shows "404 - File or directory not found." error. * I have investigated this problem and tried to find alternative url. * Unfortunately I couldn't find any related url(s). | na | 2013-02-20 | ok
8 | SYS-6760 | us_wv_sex_offenders.groovy | 2013-02-19 | SYS-6760 us_wv_sex_offenders - IMPORT_FAILURE - 2012/12/22 13:00:01:712 EST java.lang.Exception: Error invoking[http://www.wvstatepolice.com/sexoff/mainsearch_r07.cfm] HTTP/1.1 404 NOT FOUND | na | * Index url update. * Regex fixes for Imgurl and addressess. * Works fine now. | na | 2013-02-22 | ok
9 | SYS-6763 | us_ga_sex_offenders.groovy | 2013-02-19 | SYS-6763 us_ga_sex_offenders - IMPORT_FAILURE java.lang.Exception: Validation Errors Occurred:[Entity[TIMOTHY LEDBETTER]Property[event.date]:Invalid date exception[00//0000]:Unparseable date: "00//0000"]] | na | * Fixed validation error. * Img url is now captured. * Works fine. | na | 2013-02-25 | ok
10 | SYS-7221 | us_me_sex_offenders.groovy | 2013-02-22 | SYS-7221 us_me_sex_offenders - IMPORT_FAILURE java.lang.NullPointerException: Cannot invoke method getAt() on null object at us_me_sex_offenders.handleEntityPage(us_me_sex_offenders:56) at us_me_sex_offenders$_handleLastNamePage_closure1.doCall(us_me_sex_offenders:30) at us_me_sex_offenders.handleLastNamePage(us_me_sex_offenders:26) | na | * Html changed, so I have to edit code portions. * Works fine now. | na | 2013-02-26 | ok
11 | SYS-6797 | rba_annex.groovy | 2013-02-25 | SYS-6797 rba_annex - IMPORT_FAILURE java.lang.Exception: Error invoking[http://www.rba.gov.au/mkt-operations/fin-sanctions/xls/consolidated-list.xls] HTTP/1.1 404 Not Found | na | * Investigated the problem. * But unfortunately I couldn't find any equivalent url as code suggests. | na | 2013-02-27 | ok
12 | SYS-6802 | nv_gaming_wanted.groovy baseUrl="http://gaming.nv.gov/" | 2013-02-25 | SYS-6802 nv_gaming_wanted - IMPORT_FAILURE java.lang.Exception: Error invoking[http://gaming.nv.gov/wanted_main.htm] HTTP/1.1 404 Not Found | na | * Index url changed. * Found url: http://gaming.nv.gov/index.aspx?page=74 * But it shows error: "This page has been temporarily disabled. Please check back later for updates." | na | 2013-02-27 | ok

## jan-2013
Project Name | RDC-Java |  |  | Status Update Chart
SL | Ticket ID | Ticket Name/Parameter | Assign Date | Problem Description | Reason | Action | Additional Comment | Last Submit Date | Status | Client Comment
1 | ncua_administrative_orders | ncua_administrative_orders.groovy indexUrl="http://www.ncua.gov/Legal/Regs/Pages/AO2012.aspx" year="2012" | 2013-01-03 | I believe Anne means ncua_administrative_orders.groovy script for 2012. Corresponding URL is in Anne's comment below. " I discovered today that our scraper for "Ntnl Credit Union Administration Admin Orders 2012" has only captured two entity names - but there are many more names at the source URL - http://www.ncua.gov/Legal/Regs/Pages/AO2012.aspx - than that. Can we fix this scraper please? Thanks." | na | * Script parameter index url changed to : "http://www.ncua.gov/Legal/Regs/Pages/AO2012.aspx" * ie. replaceAll(/(Pages)/, 'Regs/'+'$1') | na | 2013-01-04 | ok
2 | SYS-5930 | chicago_most_wanted.groovy | 2013-01-02 | SYS-5930 chicago_most_wanted - IMPORT_FAILURE - 2012/09/19 18:00:00:647 EDT org.apache.commons.httpclient.CircularRedirectException: Circular redirect to 'http://www.chicagopolice.org:80/mostwanted/Default.aspx' | na | * Old index url is updated to new one because - Old one doesn't contain all entity - Sometimes returns "An error occurred while processing your request" error. * Because of url update, preety good amount of codes needed to be changed. * It works fine now. | na | 2013-01-08 | ok
3 | SYS-5941 | forfeiture_gov.groovy archiveDirectory="/SG/rep_Internal_Data/Web_Archive/forfeiture.gov/" archiveUrl="http://w-tlapp02.rdc.com/SG/rep_Internal_Data/Web_Archive/forfeiture.gov/100c1d0848c40504.html" | 2013-01-02 | SYS-5941 forfeiture_gov - IMPORT_FAILURE - 2012/09/20 08:00:00:534 EDT org.apache.commons.httpclient.ConnectTimeoutException: The host did not accept the connection within timeout of 5000 ms | na | * Existing code works fine here. * Timeout exception might heve occured by server related issues. * But this script has an old problem which is - It fails to access "archiveUrl" at my machine which only executes in wednessday. * You can reproduce this problem by commenting line 38. | na | 2013-01-09 | ok
4 | SYS-5959 | unseccouncil1267_list.groovy | 2013-01-02 | SYS-5959 UNSECCOUNCIL1267_LIST java.io.FileNotFoundException: http://www.un.org/sc/committees/1267/consolidatedlist.xml UNSECCOUNCIL1267_LIST.run(UNSECCOUNCIL1267_LIST:12) | na | * Index url updated. | na | 2013-01-03 | ok
5 | SYS-6253 | us_nh_sex_offenders.groovy | 2013-01-02 | SYS-6253 us_nh_sex_offenders - IMPORT_FAILURE - 2012/12/09 23:00:01:570 EST java.lang.Exception: java.util.regex.Matcher[pattern=<br>(.*?) \p{Upper}{2}, region=0,20 lastmatch=] at us_nh_sex_offenders.scrapeCity(us_nh_sex_offenders:186) | na | * Regex fix | na | 2013-01-07 | ok
6 | SYS-6308 | us_fl_most_wanted.groovy | 2013-01-02 | SYS-6308 us_fl_most_wanted - IMPORT_FAILURE - 2012/12/11 05:20:53:188 EST org.apache.commons.httpclient.ConnectTimeoutException: The host did not accept the connection within timeout of 10000 ms | na | * Exsisting code works fine here. * Timeout exception might heve occured by server related issues. | na | 2013-01-08 | ok
7 | SYS-6854 | fbi_generic_wanted.groovy indexUrl="http://www.fbi.gov/wanted/cac" | 2013-01-02 | SYS-6854 fbi_fugitives_crimes_against_children - IMPORT_FAILURE - 2013/01/01 05:13:48:260 EST java.lang.Exception: Validation Errors Occurred:[Entity[JEFFREY DEAN MCDANIEL]Property[ScarsMarks]:Invalid length[837] - greater than[500] - Value:McDaniel has the following tattoos: several skulls, one wearing a helmet, and 3" roses on vines on his chest; a solar system design featuring multicolored planets from his wrist to his elbow on his left forearm; an Egyptian pharaoh on his right bicep; a door hinge on the inside of his right elbow; old swastikas on both forearms (blacked over, but still visible); a dagger on his left wrist with "S" and "J" on either side of it; lightning bolts on the fingers of his left hand; a green wedding band on his left ring finger over the word "Michelle"; a dot on the web of his right hand; "X" inside a circle on the inside of the web of his left hand; a snake winding through a skull on his right calf; "Shelly" above his right knee; "MBM" in Old English letters above his left knee; and the image of Fred Flintstone elsewhere on his body.] | na | * "Scar Marks" entities whose length are greater than 500 characters are trimmed to 497+"..." characters as other instances of entities length truncation in script. * ie: replaceAll(/(?:.*?:\s*)?(.{497}).*/,'$1'+'...')) | na | 2013-01-04 | ok
8 | SYS-6765 | dea_criminal_cases_against_doctors.groovy | 2013-01-09 | SYS-6854 fbi_fugitives_crimes_against_children - IMPORT_FAILURE - 2013/01/01 05:13:48:260 EST SYS-6765 dea_criminal_cases_against_doctors | na | * Few regex fixes * Works fine now | na | 2013-01-10 | ok
9 | SYS-6795 | nj_ccc_excluded_persons.groovy | 2013-01-09 | SYS-6795 nj_ccc_excluded_persons Here is relevant URLs for the ticket http://www.state.nj.us/casinos/exclusion/ and http://www.nj.gov/oag/ge/exclusion/exclusion_photoindex/photoindex.htm | na | * Added pdf file handler for entity parsing. * Few regexp fixes. | na | 2013-01-15 | ok
10 | SYS-6857 | cfsp.groovy | 2013-01-09 | SYS-6857 CFSP_LIST - IMPORT_FAILURE org.xml.sax.SAXParseException: The element type "NAME" must be terminated by the matching end-tag "</NAME>". CFSP_LIST.run(CFSP_LIST:8) | na | * Works fine here and returns 2397 entities. * It seems that, "NAME must be terminated by the matching end-tag </NAME>" problem might have caused by incomplete xml file even though I don't understand how this could happen. | na | 2013-01-15 | ok
11 | SYS-6909 | cia_political.groovy type="partiesAndLeaders" | 2013-01-09 | SYS-6909 cia_political_parties_and_leaders - IMPORT_FAILURE java.lang.Exception: Validation Errors Occurred:[Entity[]Property[name]:Required field] | na | * Works fine here. * This is an old problem which I don't get at my side. * Similar problem was solved once by "StringUtils.isBlank" check in line 112 in current version. | na | 2013-01-15 | ok
12 | SYS-6799 | us_ma_sex_offenders.groovy | 2013-01-15 | SYS-6799 us_ma_sex_offenders - IMPORT_FAILURE java.lang.NullPointerException: Cannot invoke method getAt() on null object at us_ma_sex_offenders.handleEntityPage(us_ma_sex_offenders:67) I am attaching script here. If HTML changed for that site please rewrite this script and throw away LabelValueParser. Also please use def addr = entity.newAddress(), entity.newEvent() rather than ScrapeEvent event = new ScrapeEvent() etc... | na | * Just a regexp fix. * In line 38 , tr.stripXmlAttributes() is replaced by "replaceAll(/(<[\w]+)([^>]*)/, '$1')" * I could have optimized the script at further level but in that case I'd have to change good amount of codes. * Because of "minimal code change" guide line, I didn't change codes for optimizations but for exceptions. * Works fine now. | na | 2013-01-18 | ok
13 | SYS-6880 | colorado_real_estate.groovy indexUrl="http://www.dora.state.co.us/Real-estate/real_estate/disciplinary_action2007.htm" | 2013-01-16 | SYS-6880 colorado_real_estate_2007 - IMPORT_FAILURE java.lang.NullPointerException | na | * Index url redirect to http://www.colorado.gov/.... * But "colorado.gov" returns nothing(time out) both in browser and script. | na | 2013-01-18 | ok
14 | SYS-6910 | us_most_wanted_alabama.groovy | 2013-01-16 | SYS-6910 us_most_wanted_alabama - IMPORT_FAILURE org.apache.commons.httpclient.ConnectTimeoutException: The host did not accept the connection within timeout of 10000 ms | na | * Index url updated. * Few regexp + other fixes | na | 2013-01-18 | ok
15 | SYS-6917 | us_ncdoj_most_wanted.groovy | 2013-01-16 | SYS-6917 - please research URL and see if HTML is the same, if not please rewrite the script. us_ncdoj_most_wanted java.lang.Exception: Error invoking[http://www.ncdoj.com/Crime/Solve-Crimes/SBI-Most-Wanted.aspx] HTTP/1.1 404 Not Found | na | * Updated index url but not sure if that is the correct url. * Unicode chrs in url are ecoded which was creating problems previously. * Works fine now. | na | 2013-01-17 | ok
16 | SYS-6735 | mi_most_wanted_escapees.groovy | 2013-01-19 | SYS-6735 mi_most_wanted_escapees - IMPORT_FAILURE here is relevant URL. http://www.michigan.gov/msp/0,1607,7-123-1589_31786_54761_54763---,00.html If HTML changed feel free to rewrite script from scratch. | na | * Index URL updated. * Because of html changes, good amount of codes were changed. | na | 2013-02-07 | ok
17 | SYS-7063 | tx_securities_board_civil_criminal.groovy indexUrl="http://www.ssb.state.tx.us/Enforcement/2012_Civil_and_Criminal_Actions.php" year="2012" | 2013-01-22 | SYS-7063 Broken - Scraper - TX Securities Board Civil and Criminal Actions 2012 tx_securities_board_civil_criminal_2012 Source URL http://www.ssb.state.tx.us/Enforcement/2012_Civil_and_Criminal_Actions.php | na | * Few Regexp fix because of html updates. | na | 2013-01-23 | ok
18 | SYS-7064 | wisconsin_mortgage_orders.groovy indexUrl="http://www.wdfi.org/newsroom/admin_orders/mb_default.htm" | 2013-01-22 | SYS-7064 Broken Scraper - WI Mortgage Banking Administrative Orders 2012 wisconsin_mortgage_orders_2012 Source URL http://www.wdfi.org/newsroom/admin_orders/mb_default.htm | na | * Index url doesn't show anything both in browser and script. * Most probably their server is down. | na | 2013-01-23 | ok
19 | SYS-7048 | us_ct_securities_orders.groovy indexUrl="http://www.ct.gov/dob/cwp/view.asp?a=2246&q=428178" year="2009" | 2013-01-29 | SYS-7048 us_ct_consumer_orders_2009 - IMPORT_FAILURE java.io.FileNotFoundException: /SG/Internal_Data/List_Importer/data/us_ct_consumer_orders_2009/2013.01.22.03.00.15/us_ct_consumer_orders_2009_2013.01.22.03.00.15.xml (No such file or directory) | na | * The script currently I have, doesn't work with the file or directory named "/SG/Internal_Data/.." or anything like that as exception refers. * So I don't understand how this exception happens. * Other than that, I fixed entity url syntax to capture url in correct form. * I have attached the current fixed script. | na | 2013-01-30 | ok
20 | SYS-7116 | us_ny_banking_suspensions.groovy | 2013-01-29 | SYS-7116 us_ny_banking_suspensions - IMPORT_FAILURE java.lang.Exception: Error invoking[http://www.banking.state.ny.us/eambsusp.htm] HTTP/1.1 404 Not Found | na | * Index url updated. * Works fine now. | na | 2013-01-30 | ok